INSTANTSITE

Technical Scope of Work

Laravel Upgrade &

shadcn-vue UI Rebuild

Version 1.0

April 2026

| Document Type | Technical Scope of Work |
| --- | --- |
| Project | InstantSite — Laravel Upgrade & shadcn-vue UI Rebuild |
| Date | April 2026 |
| Version | 1.0 |
| Status | Draft for Review |

# 1. Executive Summary

This document defines the scope of work to upgrade the InstantSite platform's application shell to the latest stable versions of Laravel and its PHP dependencies, and to consolidate the frontend UI layer onto a single, consistent component system built on shadcn-vue.

The current application mixes three UI libraries — shadcn-vue, Flowbite Vue, and Reka-UI — resulting in inconsistent design patterns, duplicated logic, and an increased maintenance burden. The goal of this rebuild is a clean, unified component system that is accessible by default, easy to theme, and straightforward for any developer to extend.

The generated one-page business websites (the public-facing output of the platform) are explicitly out of scope — they have their own design language and must not be affected by this work.

# 2. Current State

## 2.1 Tech Stack

The platform currently runs on the following stack:

| Layer | Technology |
| --- | --- |
| Backend | Laravel 12, PHP 8.2+ |
| Frontend | Vue 3 (Composition API) + TypeScript 5.2 |
| Build | Vite 7 with Laravel Vite Plugin |
| Styling | Tailwind CSS 4.1 |
| UI Libraries | shadcn-vue, Reka-UI, Flowbite Vue, Lucide Icons |
| Routing | Inertia.js (server-driven) |
| Database | SQLite (dev), MySQL/PostgreSQL (prod) |
| Queue | Laravel database queue with job batching |
| Auth | Laravel Sanctum + session-based auth |
| Notifications | vue-sonner (toast) |
| Testing | Pest PHP 4, PHPUnit |

## 2.2 UI Library Problem

The current frontend uses three overlapping component libraries simultaneously. This creates several problems:

- Inconsistent visual style — Flowbite and shadcn-vue components look noticeably different without heavy custom CSS.

- Accessibility gaps — Flowbite Vue does not provide the same level of ARIA support as Reka-UI-backed shadcn-vue components.

- Bundle bloat — all three libraries are shipped to the client even when only a subset of components from each is used.

- Developer friction — contributors must learn three different component APIs and prop conventions.

- Theming complexity — maintaining a consistent dark/light mode across three libraries requires extensive CSS overrides.

# 3. Objectives

- Upgrade Laravel and all PHP dependencies to the latest stable patch releases.

- Upgrade Node, npm, and all JavaScript dependencies to current stable versions where possible.

- Remove Flowbite Vue and Reka-UI from the project's direct dependencies.

- Rebuild or replace every application UI component using shadcn-vue primitives.

- Preserve all existing functionality, routes, and user flows without visible regression.

- Ensure dark/light/system theme support works correctly across all rebuilt components.

- Maintain or improve current Lighthouse accessibility scores.

- Leave the generated one-page business websites completely untouched.

# 4. Scope of Work

## 4.1 In Scope — Application Shell

The following areas of the application are in scope for the UI rebuild:

| Area / Page | Current Library | Target (shadcn-vue) | In Scope |
| --- | --- | --- | --- |
| Landing page (Welcome.vue) | Flowbite Vue + custom CSS | shadcn-vue Card, Input, Button, Badge | Yes |
| Place search autocomplete | Custom + Flowbite | shadcn-vue Command / Popover | Yes |
| Discover loading screen | Custom CSS | shadcn-vue Skeleton, Progress | Yes |
| Setup wizard (logo, description) | Flowbite Vue forms | shadcn-vue Form, Input, Textarea, Label | Yes |
| Preview page | Mixed | shadcn-vue Card, Tabs | Yes |
| Dashboard — Overview tab | Flowbite Vue cards | shadcn-vue Card, Badge, Separator | Yes |
| Dashboard — Site Settings tab | Flowbite Vue + custom | shadcn-vue Form, RadioGroup, Input | Yes |
| Dashboard — Components tab | Flowbite Vue | shadcn-vue Accordion, Card, Switch | Yes |
| Dashboard — Settings tab | Flowbite Vue | shadcn-vue Form, Input, Button | Yes |
| Auth pages (Login, Register, Reset) | Flowbite Vue forms | shadcn-vue Form, Input, Button, Alert | Yes |
| Email verification pages | Custom | shadcn-vue Alert, Button | Yes |
| User Settings (Profile, Password) | Flowbite Vue | shadcn-vue Form, Input, Button, AlertDialog | Yes |
| Appearance settings | Custom composable + custom CSS | shadcn-vue ToggleGroup, Label | Yes |
| Toast notifications | vue-sonner | vue-sonner (keep — integrates with shadcn-vue) | Yes |
| Global layout / AppLayout | Mixed | shadcn-vue Sidebar, NavigationMenu | Yes |

## 4.2 Explicitly Out of Scope

OUT OF SCOPE — Generated Websites

The generated one-page business websites (resources/js/pages/site/ and resources/js/components/site/) must not be touched.

These pages have their own standalone design language and are rendered for end-customers, not platform users.

Any change to these files — even dependency-level changes — is out of scope for this engagement.

Additionally, the following are out of scope:

- Backend Laravel application logic, controllers, models, and jobs.

- Database schema changes (no new migrations required).

- API route changes.

- Deployment infrastructure or CI/CD pipeline changes (beyond updating Node/PHP version pins if required).

- New features or functionality not present in the current system.

# 5. Technical Approach

## 5.1 Phase 1 — Dependency Audit & Upgrade

Before any UI work begins, all dependencies are audited and upgraded to reduce the risk of breakages during the component rebuild.

| # | Task | Detail | Effort (est.) |
| --- | --- | --- | --- |
| 1.1 | Audit current dependency versions | Run composer outdated and npm outdated; produce a versioned diff report. | 0.5 days |
| 1.2 | Upgrade PHP dependencies | Upgrade Laravel and all first-party packages (Sanctum, Inertia, Pest) to latest stable. | 0.5 days |
| 1.3 | Upgrade JS dependencies | Upgrade Vite, Vue, TypeScript, Tailwind, ESLint, and related tooling. | 0.5 days |
| 1.4 | Remove Flowbite Vue | Uninstall flowbite-vue and flowbite from package.json; confirm no compile errors. | 0.5 days |
| 1.5 | Remove standalone Reka-UI imports | shadcn-vue already bundles Reka-UI; remove any direct reka-ui imports and deduplicate. | 0.5 days |
| 1.6 | Run full test suite | Execute composer test and npm run lint; fix any regressions before proceeding to Phase 2. | 0.5 days |

## 5.2 Phase 2 — shadcn-vue Component Audit

Map every UI component currently in use to a shadcn-vue equivalent. Where a component does not yet exist in shadcn-vue, identify whether it can be composed from existing primitives or requires a custom implementation.

| # | Task | Detail | Effort (est.) |
| --- | --- | --- | --- |
| 2.1 | Audit existing components | List every component in components/ui/, components/dashboard/, components/setup/, and pages/. | 1 day |
| 2.2 | Map to shadcn-vue equivalents | Produce a component mapping document: existing → shadcn-vue target. | 0.5 days |
| 2.3 | Add missing shadcn-vue components | Run npx shadcn-vue@latest add <component> for any required components not yet installed. | 0.5 days |
| 2.4 | Identify custom components | Flag anything that requires bespoke implementation (e.g. place search autocomplete, image upload). | 0.5 days |

## 5.3 Phase 3 — UI Rebuild

Rebuild each in-scope area systematically, page-by-page. All form handling continues to use Inertia's useForm; only the presentational layer changes.

| # | Task | Detail | Effort (est.) |
| --- | --- | --- | --- |
| 3.1 | Global layout & navigation | Rebuild AppLayout using shadcn-vue Sidebar and NavigationMenu components. | 1 day |
| 3.2 | Shared UI primitives | Audit and clean up components/ui/ — remove Flowbite-based overrides, keep shadcn-vue versions. | 0.5 days |
| 3.3 | Auth pages | Login, Register, Forgot Password, Reset Password, Email Verification. | 1 day |
| 3.4 | User Settings pages | Profile, Password, Appearance — all three settings pages. | 0.5 days |
| 3.5 | Landing page (Welcome.vue) | Search input, results list, hero section. | 1 day |
| 3.6 | Discover loading screen | Progress indicator, skeleton loaders. | 0.5 days |
| 3.7 | Setup wizard | Logo upload, description, social links, quick links form. | 1 day |
| 3.8 | Preview page | Tabbed layout showing site preview with call-to-action. | 0.5 days |
| 3.9 | Dashboard — Overview | Stats cards, site status, quick-action buttons. | 0.5 days |
| 3.10 | Dashboard — Site Settings | Domain type selector (RadioGroup), subdomain/custom domain inputs, meta fields. | 1 day |
| 3.11 | Dashboard — Components | Toggle components on/off (Switch), accordion for configuration. | 1 day |
| 3.12 | Dashboard — Settings | Global site settings form. | 0.5 days |

## 5.4 Phase 4 — QA & Accessibility

| # | Task | Detail | Effort (est.) |
| --- | --- | --- | --- |
| 4.1 | Cross-browser testing | Chrome, Firefox, Safari — all in-scope pages. | 1 day |
| 4.2 | Dark / light / system theme | Verify theme switching works correctly on every rebuilt page. | 0.5 days |
| 4.3 | Keyboard navigation audit | Tab order, focus rings, ARIA labels — all interactive components. | 0.5 days |
| 4.4 | Responsive layout check | Mobile (375px), tablet (768px), desktop (1280px) breakpoints. | 0.5 days |
| 4.5 | Regression testing | Walk through the full user flow: search → discover → setup → preview → register → dashboard. | 0.5 days |
| 4.6 | Lint & type-check | npm run lint and tsc --noEmit must pass with zero errors. | 0.5 days |
| 4.7 | Pest test suite | composer test must pass with no regressions. | 0.5 days |

# 6. Key Component Mappings

The table below summarises the most significant component substitutions:

| Current | Replacement | Notes |
| --- | --- | --- |
| Flowbite Input | shadcn-vue Input | Drop-in replacement; Inertia useForm bindings unchanged |
| Flowbite Button | shadcn-vue Button | Variant prop maps 1:1 (primary, secondary, destructive) |
| Flowbite Dropdown | shadcn-vue DropdownMenu | Reka-UI based; fully keyboard accessible |
| Flowbite Modal | shadcn-vue Dialog | Reka-UI Dialog — focus trap included |
| Flowbite Tabs | shadcn-vue Tabs | Reka-UI Tabs with animated indicator |
| Flowbite Badge | shadcn-vue Badge | Utility variants (default, secondary, destructive, outline) |
| Flowbite Card | shadcn-vue Card | CardHeader, CardContent, CardFooter sub-components |
| Flowbite Select | shadcn-vue Select | Reka-UI Select — accessible with search |
| Flowbite Checkbox | shadcn-vue Checkbox | Reka-UI Checkbox with proper indeterminate state |
| Flowbite Radio | shadcn-vue RadioGroup | Used for domain type selector on Site Settings |
| Flowbite Toggle | shadcn-vue Switch | Used for component on/off toggles in dashboard |
| Flowbite Alert | shadcn-vue Alert | AlertTitle + AlertDescription sub-components |
| Flowbite Textarea | shadcn-vue Textarea | Drop-in replacement |
| Custom file upload | shadcn-vue + custom | Compose from Button + hidden input; no library swap needed |
| Custom place search | shadcn-vue Command | Popover + CommandInput + CommandList for autocomplete |
| Custom confirm dialog | shadcn-vue AlertDialog | Used for destructive actions (account deletion, etc.) |

# 7. Effort Estimate

The following is a summary of estimated effort across all phases:

| Phase | Description | Est. Days |
| --- | --- | --- |
| Phase 1 | Dependency Audit & Upgrade | 3 days |
| Phase 2 | shadcn-vue Component Audit | 2.5 days |
| Phase 3 | UI Rebuild (all in-scope areas) | 9 days |
| Phase 4 | QA & Accessibility | 4 days |
| Buffer | 10% contingency | 1.5 days |
| TOTAL |  | 20 days |

ASSUMPTIONS

Estimates assume a single mid-to-senior frontend developer familiar with Vue 3 and Tailwind CSS.

Estimates do not include project management, code review, or stakeholder feedback cycles.

Backend developer involvement is expected to be minimal (< 1 day) — primarily for environment and dependency updates.

# 8. Risks & Mitigations

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Flowbite component removal breaks pages not in the component audit | Medium | High | Perform a grep-based audit for all flowbite-vue imports before removing the package. |
| shadcn-vue equivalent does not yet exist for a required component | Low | Medium | Compose from Reka-UI primitives directly; shadcn-vue is already built on these. |
| Inertia.js upgrade introduces breaking changes to useForm or shared props | Low | High | Pin Inertia to current major version for Phase 1; upgrade in isolation if needed. |
| Tailwind 4 configuration incompatibilities after dependency upgrades | Medium | Medium | Run full lint + visual diff after each upgrade step; revert via git if needed. |
| Generated websites accidentally broken by global CSS changes | Low | High | Add automated screenshot regression tests for site/Index.vue before work begins. |
| Dark mode regression after component replacements | Medium | Medium | Test dark mode after every rebuilt page as part of Phase 3, not just Phase 4. |

# 9. Dependencies & Prerequisites

- Access to the InstantSite Git repository with a feature branch strategy (recommended: feature/shadcn-rebuild).

- A valid Google Places API key in .env for end-to-end testing of the full user flow.

- Node.js 22 LTS and PHP 8.2+ on the development machine.

- All four dev processes running concurrently during testing (php artisan serve, queue:listen, pail, npm run dev).

- Wildcard DNS or /etc/hosts entries for *.instantsite.test pointing to 127.0.0.1.

# 10. Acceptance Criteria

The engagement is considered complete when all of the following criteria are met:

| # | Acceptance Criterion |
| --- | --- |
| AC-01 | No import of flowbite-vue or standalone reka-ui packages exists anywhere in resources/js/. |
| AC-02 | All in-scope pages render correctly in Chrome and Firefox at mobile, tablet, and desktop breakpoints. |
| AC-03 | Light mode, dark mode, and system theme all apply correctly to every in-scope page. |
| AC-04 | The full user flow completes without error: search, discover, setup, preview, register, dashboard. |
| AC-05 | npm run lint returns zero errors or warnings. |
| AC-06 | tsc --noEmit returns zero TypeScript errors. |
| AC-07 | composer test passes with no regressions. |
| AC-08 | The generated one-page business website renders identically before and after the work. |
| AC-09 | All interactive components are operable via keyboard alone (tab, enter, escape, arrow keys). |
| AC-10 | A visual review sign-off has been obtained from the product owner. |

# 11. Appendix — Relevant Files

The following files are the primary targets for Phase 3 of the rebuild:

| File Path | Phase 3 Task |
| --- | --- |
| resources/js/pages/Welcome.vue | 3.5 — Landing page |
| resources/js/pages/preview/Discover.vue | 3.6 — Loading screen |
| resources/js/pages/preview/Setup.vue | 3.7 — Setup wizard |
| resources/js/pages/preview/Index.vue | 3.8 — Preview page |
| resources/js/pages/Dashboard.vue | 3.9–3.12 — Dashboard |
| resources/js/pages/auth/Login.vue | 3.3 — Auth |
| resources/js/pages/auth/Register.vue | 3.3 — Auth |
| resources/js/pages/auth/ForgotPassword.vue | 3.3 — Auth |
| resources/js/pages/auth/ResetPassword.vue | 3.3 — Auth |
| resources/js/pages/auth/VerifyEmail.vue | 3.3 — Auth |
| resources/js/pages/settings/Profile.vue | 3.4 — Settings |
| resources/js/pages/settings/Password.vue | 3.4 — Settings |
| resources/js/pages/settings/Appearance.vue | 3.4 — Settings |
| resources/js/components/dashboard/* | 3.9–3.12 — Dashboard |
| resources/js/components/setup/* | 3.7 — Setup wizard |
| resources/js/components/ui/* | 3.2 — Shared primitives |
| resources/js/layouts/AppLayout.vue | 3.1 — Global layout |

End of Document — InstantSite Technical Scope of Work v1.0